## Slide 1: WP4 AHM
WP4 members
Notes: Añadir logo de IBERGRID

## Slide 2: Workplan
[M1-M6] Task 4.1. Services and Best Practices harmonisation. UPV (10), CSIC-IFCA (2), CSIC-CNB (2), CSIC-BSC (2), CSIC-CIEMAT (2), LIP (1), KIT (2), CESNET (2), IISAS (1), IRD (2), LNEC (4), INDRA (2)
[M7-M24] Task 4.2. Thematic Services for the EOS community. LNEC (37), LIP (7), IRD (16), UPV (5), INDRA (18)
[M7-M24] Task 4.3. Thematic Services for the Biomedicine community. CSIC-CNB (12), CSIC-BSC (10), CESNET (5), UPV (3)
[M7-M24] Task 4.4. Thematic Services for the Astrophysics community. CSIC-CIEMAT (18), UPV (3)
[M7-M24] Task 4.5. Thematic Services for the Environmental community. CSIC-BSC (8), KIT (10), CESNET (6), IISAS (7)
[M18-M30] Task 4.6. Thematic Services Validation. UPV (9), CSIC-CNB (4), CSIC-BSC (4), CSIC-CIEMAT (4), LIP (2), KIT (3), CESNET (2), IISAS (2), IRD (2), LNEC (6), INDRA (4)
D4.1 – Best Practices Elicitation including Data Management Plans (R, PU) – M6 – Lead: UPV
D4.2 - First prototype of the EOSC Thematic services (DEM, PU) – M16 – Lead: UPV

## Slide 3: What have we done so far?
Present the objective of the WP
  Define Best Practice for the adoption of EOSC services.
  Improve the thematic services through the adoption of the EOSC services.
Collect and present a brief description of use cases including target users, objectives of the service, bottlenecks and data sources (https://indico.lip.pt/event/575/sessions/317/#20190924)
Start collecting ideas for metrics
  Improvement in Users, Capacity & Capability, Scientific Impact and Outreach, Usability (Qualitative).
  https://indico.lip.pt/event/575/sessions/319/#20190924
Define a set of actions (see next slide).

## Slide 4: What we have to do shortly?
# | Description | Who | Due Date
1 | Collect google accounts for WP4 memebers email -> ibespert@gmail.com | All | 
2 | Create mailing lists, populate permissions for Drive, create “taco” in Trello | Ignacio | 
3 | Collect detailed descriptions of Thematic Services https://docs.google.com/document/d/1JrWG7ZrgdodjI7WlScPJMuRG9ZmTatw3A4n7mufJ9ws/edit# | All | 
4 | Agree on the fields to be collected for the technology solutions of thematic services https://docs.google.com/spreadsheets/d/13IFtOTRF_33c9BQRS803sJ9uVafMQzkVFc5ptVVoY2Y/edit#gid=0 | All | 
5 | Collect technology solutions as above | All |